## Slide 1
PHASE 5: CLOSING
Lekope FM Financial Management System
Project Management Life Cycle – Final Phase
16 Deliverables
All Completed
14 Weeks
On Schedule
150 Hours
Total Effort
6 Objectives
All Achieved
BISP4112 • Software Project Management • Limkokwing University of Creative Technology

## Slide 2
What is Phase 5: Closing?
The final stage of the Project Management Life Cycle — formally wrapping up the project with evidence and reflection.
✓ Confirm Completion
Verify all deliverables across all 5 phases have been completed and accepted.
📊 Evaluate Performance
Measure actual schedule and effort against the original project plan.
💡 Capture Lessons Learned
Document what worked, what failed and what the team would do differently.
🔄 Transfer Knowledge
Hand over all project artefacts and insights to relevant stakeholders.

## Slide 3
5.1.1 Deliverables Completion Checklist
All 16 deliverables across 5 phases — 100% complete
Phase 1
Initiation
Project Charter
Stakeholder Register
Business Case
✓ All Done
Phase 2
Planning
SRS · WBS · Gantt
Risk Register
Comm. Plan · RACI
✓ All Done
Phase 3
Execution
Resource Allocation
Prototype / UI Mockups
✓ All Done
Phase 4
Monitoring
Status Reports
Test Plan
✓ All Done
Phase 5
Closing
Closure Report
Lessons Learned
Final Presentation
✓ All Done
Every deliverable met the marking rubric requirements — SRS (6 sections), WBS (3 levels), Risk Register (7 risks), Gantt Chart aligned to SDLC phases.

## Slide 4
5.1.2 Project Objectives Evaluation
Automate income recording
Income module with full CRUD & PDF export
✓
Automate expense recording
5 categories with form validation
✓
Generate financial reports
Multiple report types with PDF export
✓
Role-based access control
5 roles implemented (exceeded target of 3)
✓
Improve financial transparency
Real-time dashboard with 4 key metrics
✓
Audit trail
Audit log designed in DB schema & flowchart
✓
Objective
Outcome
Status

## Slide 5
5.1.3 & 5.1.4 Schedule & Resource Performance
Schedule Performance
Project Charter & SRS
Wk 8
Wk 8
✓
WBS, Gantt, Risk Register
Wk 9
Wk 9
✓
RACI & Comms Plan
Wk 9
Wk 9
✓
Resource Allocation
Wk 10
Wk 10
✓
UI Wireframes & Prototype
Wk 10
Wk 11
+1
Test Plan
Wk 12
Wk 12
✓
Closure & Lessons Learned
Wk 14
Wk 14
✓
Planned
Actual
Resource Effort (Hours)
Project Manager
44h
46h
Business Analyst
30h
30h
System Designer
38h
42h
Developer
14h
14h
QA
18h
18h
Planned
Actual (on/under)
Over
Total: 144h planned → 150h actual (+4.2% — within acceptable range)

## Slide 6
5.2.1 Lessons Learned — What Went Well
✓ Project Planning
Detailed WBS eliminated ambiguity — who owns what was always clear.
✓ Requirements (SRS)
Completed by Week 4; prevented scope creep and anchored the test plan.
✓ Team Communication
WhatsApp daily + Monday meetings — no major breakdowns occurred.
✓ Prototype Quality
Working prototype with live data exceeded wireframe expectations.
✓ Risk Management
Risk register directly prevented a schedule delay in Week 10.
✓ Gantt Discipline
Referenced every week in Monday meetings; on schedule 13 of 14 weeks.

## Slide 7
5.2.2 What Didn't Go Well & How It Was Managed
⚠ Prototype Delay (Wk 10–11)
Issue: Reports wireframe not done by Week 10 — stakeholder feedback required extra revision.
→ Fix: Review extended to Week 11; PM redistributed tasks. No final deadline impact.
💡 Build buffer into UI tasks — iterations should be planned, not assumed.
⚠ Team Member Unavailability
Issue: One member unavailable two days in Week 10.
→ Fix: Risk plan R1 activated; tasks redistributed thanks to cross-training.
💡 Cross-train early — never leave one person as the sole owner of a task.
⚠ Effort Underestimation (Design)
Issue: PERT chart, flowchart and DB schema took 4 more hours than estimated.
→ Fix: Designer absorbed extra effort; no de-scoping.
💡 Add 20–30% buffer to all design task estimates.
⚠ Typo in IT-01 Test Case
Issue: 'Augh' instead of 'Auth' not caught in first review.
→ Fix: Corrected before submission; peer review checklist added.
💡 Every deliverable needs a peer review by a second team member.

## Slide 8
5.2.3 Recommendations for Future Projects
01
Start the SRS early — solid requirements prevent all downstream confusion.
02
Use a real PM tool (Monday.com / Trello / Jira) from Day 1, not Week 10.
03
Assign a dedicated peer reviewer for every deliverable — not the author.
04
Add one week of buffer before major deadlines for design-heavy deliverables.
05
Run 15-minute daily stand-ups during peak weeks (Weeks 9–12) to catch blockers early.
06
Document the prototype early — two full review cycles need time.
07
Complete the RACI matrix immediately after the Project Charter — clear accountability is the #1 performance factor.

## Slide 9
5.3 Final Presentation & Prototype Demo
User Registration
Registration form with 5 role options: Finance Manager, Traffic Manager, Station Manager, Sales Executive, IT Administrator.
Login & Authentication
Role-based login redirecting each user to the correct dashboard view.
Finance Dashboard
Real-time summary cards: Revenue LSL 500 · Expenses LSL 5,700 · Net Profit LSL -5,200 · Outstanding LSL 1,800.
Recent Invoices
Invoice status badges (PAID / UNPAID / OVERDUE) with overdue alert banner.
Upcoming Bookings
Booking schedule panel: advertiser names, dates, time slots and amounts.
Navigation
Role-based sidebar: Bookings · Invoices · Expenses · Payroll · Reports.
Live prototypes available at: figma.com/make/afHMP2ckDP7qbhJeGZ4SkY | figma.com/make/m8lZ9TBSgiDExYgdcbzKix

## Slide 10
5.2.4 Team Reflections
Project Manager
"Communication is the PM's primary job. The risk register saved us in Week 10 — I will write one at the start of every future project."
Business Analyst
"Writing the SRS was the most valuable exercise. Precise requirements made every downstream decision easier."
System Designer
"The flowchart and PERT chart showed me how data actually moves through a system. Build in review time when designing for stakeholders."
Software Developer
"Having a DB schema and flowchart before any code was written meant I always knew exactly what to build — no costly rework."
Quality Assurance
"UAT scenarios are far more powerful than unit tests for demonstrating value to non-technical stakeholders."

## Slide 11
Project Successfully Closed
Lekope FM Financial Management System
100%
Deliverables
Completed
6/6
Objectives
Achieved
0 days
Final
Deadline Slip
+4.2%
Effort
Variance
Thank you
BISP4112 • Software Project Management • Limkokwing University of Creative Technology